## Milestones
Example text is listed in red and can be deleted by the applicant.
Applicants are required to complete the Project Management Deliverable
The Gantt chart on the next tab is optional for projects to use.
Please refer to the guidance tab for further information about what is required.
Applicants can add in additional rows where needed and should merge the Deliverable rows once they have listed all of that deliverables tasks
|  | Target timeline |  | Task completed by: |  | Costs | Energy Redress funding | Source(s) of match funding (if applicable)
Deliverable | Task(s) | Started | Finished | Person(s) or Role | Organisation(s) | Estimated cost | Percentage of activity funded by Energy Redress | Breakdown of match funding by source and percentage
Project Management Frequency of task delivery to be determined by the project
Provide in home energy advice to 200 households | 200 home visits to provide energy advice completed | 2020-01-01 | 2020-10-31 | Energy Officer 1 | Redress Housing Association | 10000 | 75% | Housing Association core staff budget (25%)

## Gantt chart
Example text is listed in red and can be deleted by the applicant.
Projects can update the start and finish date to match their project
To update the bars on the chart, select the month cell and then fill colour
The bars in green are an example which can be deleted
|  |  |  | 2020 | [11 empty] | 2021
Deliverable | Task(s) | Start date | Finish date | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Project Management Frequency of task delivery to be determined by the project | bar: 2020 Jan to 2020 Oct
Provide in home energy advice to 200 households | 200 home visits to provide energy advice completed | 2020-01-01 | 2020-10-31 | bar: 2020 Jan to 2020 Dec

## Guidance
Project Programme Heading | Guidance notes
Deliverable | The project deliverables column should include all of the deliverables listed on the main application form. Applicants should ensure that this expanded programme is consistent with the programme submitted as part of the main application. Deliverables are key outputs from the project. The list you provide should allow the assessors of the application to understand how the project will be delivered from start to finish.
Task(s) | To achieve each deliverable, applicants will need to complete a number of tasks. In this column applicants will need to clearly and concisely list each task. Applicants can insert or delete rows depending on the number of tasks associated with each deliverable. Applicants do not need to list every small task associated with delivery, instead they should ensure that the list is kept at a level of detail that enables assessors to understand how the project will be delivered. Make sure that you have merged the deliverable cell to match the number of tasks.
Started/Finished | This is the start date and end date for each specific task. The latest end date of the tasks linked to a deliverable should be the date that deliverable is completed.
Person(s) or Role | An applicant should list the person that will deliver each task. Please remember that this might be more than one person from more than one organisation. If the person is not yet employed, an applicant should enter the role that will deliver the task (e.g. "Project Manager" or "Volunteer Energy Advisor"). An applicant will need to ensure that the division of tasks is consistent with the number of days worked (bearing in mind whether staff are full time or part time).
Organisation(s) | List the organisation that the person or role works for. Our assessors want to understand the division of labour for the project between the applicant (charity leading the application) and any project partners. This can be a contractor that is yet to be selected as part of your project. For example a project may write "Insulation main contractor" or "Insulation sub-contractor". Remember that the applicant is accountable for both the delivery of the project and for the Redress grant funding. This table can be used to explain the tasks that the applicant will deliver to demonstrate how they will maintain oversight and control of the project. This is especially important where a charity is working with non-charitable partners (who are not eligible to lead a Redress-funded project). The "Project Management" deliverable should be used to demonstrate the tasks the lead charity will carry out to maintain effective governance of the project.
Estimated cost | Applicants will need to list the cost for each task. We understand that project costs can be subject to change (for example where services have not yet been procured) and estimated costs are satisfactory. If you are unable to provide a cost for each task but know the overall cost for the deliverable, you can merge the cells and enter the overall deliverable cost instead. Applicants should ensure that the costs listed here are consistent with the budget in the main application form and the total grant being requested.
Funding percentage | Applicants should enter the percentage of the cost of each task which you intend to fund from an Energy Redress grant. If activity is fully funded by Energy Redress simply enter 100% in this column. Remember to only request Redress funding for activity that is eligible for funding under the Energy Redress Scheme, for example, referrals to an ECO provider should not be funded by Energy Redress, but could be listed as activity match-funded from elsewhere. If your project has some match funding, please use this column to ensure that it is clear to assessors which activity you would like to fund from Energy Redress and which activity will be "match-funded" from other sources.
Breakdown of match funding | If applicable, list the other (non-Redress) sources of funding being used to pay for each task or deliverable. This can include any funding from other grant or loan schemes and money from an organisation's own resources. For each source of funding applicants should state the source and percentage contribution.
Project Management Tasks to be determined by the project | All applicants will need to complete the deliverable titled "Project Management". This should list the tasks the applicant and other partners will undertake to ensure the project is managed and delivered successfully (e.g. Reporting to funder, project board and any project governance activity). This part of the plan can be used to clearly demonstrate how the lead charity and grant holder will control and remain accountable for all aspects of project delivery. The template form has some pre-populated examples of tasks, applicants can tailor these to refelect the project management processes that will be used. Applications and this attached programme, should demonstrate to an assessor the Governance that will be in place to support and ensure project delivery.